## Central_Tracker
SR.NO | Activity | Technology | Activity Driven By | Start Date | Status | Activity Description | Completion Date
1 | Selecting AUT(Application Under Test) | Project Management | All | 20/09/2022 | Completed | Exploring different websites, sources to find AUT | 20/09/2022
2 | Problem Statement | Project Management | All | 20/09/2022 | Completed | Finalizing Problem Statement | 21/09/2022
3 | Api Feasibility Check | Project Management | All | 21/09/2022 | Completed | Checking for API feasibility on different websites | 22/09/2022
4 | Git Implementation | Git | Aditya Gund | 25/09/2022 | Completed | Creating Project repository on GitHub and cloning it on PSL device. Setting project on GitHub. | 2022-03-10
5 | Manual Test Case Writing | Manual_Testing | BRS: Nikita Hanchate,Test Scenario:Nupur Komari,Aditya Gund, Test cases:Nupur Komari,Aditya Gund, ECP&BVA:Sarang Mashale, State transition & Defect report: Harshada Jeure, Execution log & Execution Doc: Aditya Gund | 21/09/2022 | Completed | Creating and writing manual test cases for the pages under testing | 26/09/2022
6 | Meeting for manual testcases query | Project Management | All | 25/09/2022 | Completed | Reviewing the Manual Test Cases | 25/09/2022
7 | Status Accounting Meeting | Project Management | All | 28/09/2022 | Completed | Status Accounting meeting | 28/09/2022
8 | Meeting for manual testcases finalization | Project Management | All | 26/09/2022 | Completed | Finalizing merged Manual Test Cases | 26/09/2022
9 | Automation Test Cases | Selenium | Disha Baba, Aishwarya Khobare, Shubham Shah, Pragati Birajdar, Sarthak Jain, NN Sarika | 26/09/2022 | Completed | Automating Manual Test Cases using Selenium with Java | 2022-03-10
10 | Creating Daily Activity Tracker | Project Management | Aishwarya Khobare, Sarang Mashale | 22/09/2022 | Completed | Creating Activity Tracker | 2022-03-10
11 | Scrum Meetings | Project Management | All | 2022-01-10 | Completed | Daily Scrum Meetings | 2022-03-10
12 | Status Accounting Meeting 2 | Project Management | All | 30/09/2022 | Completed | Review tracker, manual test cases and selenium code | 2022-03-10
13 | Rest API Implementation in Postman | Rest_API_Postman | Sarang Mashale, Harshada Jeure | 28/09/2022 | Completed | Writing Manual Test cases and automating using postman | 2022-03-10

## Project_Management
SR.NO | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
Selecting AUT
1 | Selected AUT | All | 20/09/2022 | Completed | Difficulty in Finding project satisfying all the criterias | Exhaustive Searching | 20/09/2022
Problem Statement
1 | Problem Statement(OpenCart automation testing) | ALL | 20/09/2022 | Completed |  |  | 21/09/2022
API Feasibility Check
1 | API Feasibility Check for various Websites | All | 21/09/2022 | Completed | Difficulty in Finding suitable API satisfying all the criterias | Selected suitable API after deep searching and verified by anuprita and sunil | 22/09/2022
SYNC UP Meetings
1 | Meeting for manual testcases query | ALL | 2022-03-10 | Completed | Template for merging test cases and API Feasibility | Implemented suggestions provided by Anuprita | 2022-04-10
Scrum Meetings
1 | Application & Problem statement | ALL | 20/09/2022 | Completed |  |  | 20/09/2022
2 | Application selection | ALL | 21/09/2022 | Completed |  |  | 21/09/2022
3 | Setup On PSL | ALL | 21/09/2022 | Completed |  |  | 22/09/2022
4 | Problem statement | ALL | 20/09/2022 | Completed |  |  | 21/09/2022

## Git Implementation
SR.NO | Activity | Activity Driven By | Start Date | Status | Completion Date
Git Implementation
1 | Account created on Github | Aditya Gund | 28/09/2022 | Completed | 28/09/2022
2 | Create local repository | Aditya Gund | 28/09/2022 | Completed | 28/09/2022
3 | Push the content | Aditya Gund | 29/10/2022 | Completed | 29/10/2022

## Manual Testing
SR.NO | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
Manual Test Case Writing
1 | Created manual test case for Register | Nupur Komari | 21/09/2022 | Completed | Choosing a Standarized format for writing the manual test cases | Revisited Software Testing Selfy Shot | 26/09/2022
2 | Created manual test case for Login | Nupur Komari |  | Completed | Choosing a Standardized format for writing the manual test cases | Revisited Software Testing Selfy Shot
3 | Created manual test case for Features | Aditya Gund |  | Completed | Choosing a Standardized format for writing the manual test cases | Revisited Software Testing Selfy Shot
4 | Created manual test case for Marketplace | Nupur Komari |  | Completed | Choosing a Standarized format for writing the manual test cases | Revisited Software Testing Selfy Shot
5 | Created manual test case for Blog | Aditya Gund |  | Completed | Choosing a Standardized format for writing the manual test cases | Revisited Software Testing Selfy Shot
6 | Created manual test case for Download | Aditya Gund |  | Completed | Choosing a Standardized format for writing the manual test cases | Revisited Software Testing Selfy Shot
7 | Created manual test case for Resources | Nupur Komari Aditya Gund |  | Completed | Choosing a Standarized format for writing the manual test cases | Revisited Software Testing Selfy Shot
8 | Created manual test case for Account | Nupur Komari |  | Completed | Choosing a Standardized format for writing the manual test cases | Revisited Software Testing Selfy Shot

## Selenium
SR.NO | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
Automating Test Cases
1 | Deciding which test cases to Automate | ALL | 26/09/2022 | Completed |  |  | 26/09/2022
2 | Automated manual test cases of Register page using selenium | Disha Baba | 28/09/2022 | Completed | Unable to locate captcha elements | Manually entering the captcha | 2022-03-10
3 | Automated manual test cases of Login page using selenium | Shubham Shah | 26/09/2022 | Completed |  |  | 26/09/2022
4 | Automated manual test cases of Features page using selenium | Aishwarya Khobare | 26/09/2022 | Completed |  |  | 29/09/2022
5 | Automated manual test cases of Marketplace page using selenium | Disha Baba Aishwarya Khobare | 26/09/2022 | Completed |  |  | 28/09/2022
6 | Automated manual test cases of Blog page using selenium | Disha Baba | 26/09/2022 | Completed |  |  | 2022-01-10
7 | Automated manual test cases of Downoad page using selenium | Aishwarya Khobare | 27/09/2022 | Completed |  |  | 29/09/2022
8 | Automated manual test cases of Resources page using selenium | Shubham Shah Aishwarya Khobare NN Sarika | 26/09/2022 | Completed | Unable to locate captcha elements | Manually entering the captcha | 28/09/2022
9 | Automated manual test cases of Account page using selenium | Pragati Birajdar Disha Baba Aishwarya Khobare | 29/09/2022 | Completed |  |  | 30/09/2022
10 | POM Integration | Disha Baba | 2022-03-10 | Completed

## Rest API Postman
SR.NO | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
REST API Postman
1 | GET | Sarang Mashale Harshada Jeure | 2022-03-10 | Completed |  |  | 2022-03-10
2 | PUT | Sarang Mashale Harshada Jeure |  | Completed | Unable to modify the userId in cart item | With the help of online resources
3 | POST | Sarang Mashale Harshada Jeure |  | Completed
4 | PATCH | Sarang Mashale Harshada Jeure |  | Completed
5 | SCHEMA VALIDATION | Sarang Mashale Harshada Jeure | 2022-04-10 | Completed |  |  | 2022-04-10
6 | RESPONSE VALIDATION | Sarang Mashale Harshada Jeure |  | Completed
7 | PRE-REQUEST SCRIPT | Sarang Mashale Harshada Jeure |  | Completed
8 | IMPORT,EXPORT | Sarang Mashale Harshada Jeure |  | Completed
9 | DATA DRIVEN | Sarang Mashale Harshada Jeure |  | Completed